## Sheet1
Risk Assessment/ Risk Matrices | [5 empty] | Key:
Column1 | Very Low | low | Medium Risk | Major Risk | Fatality | Low
Very Unlikely | Low | Low | Low Medium | Medium | Medium | Low Medium
Unlikely | Low | Low Medium | Low Medium | Medium | Medium High | Medium
Moderate | Low | Low Medium | Medium | Medium High | Medium High | Medium High
Likely | Low | Low Medium | Medium | Medium High | High | High
Very likely | Low Medium | Medium | Medium High | High | High
Risk | Statement | How do eliminate risk | Likelihood | Impact | Risk Level
Straining your eyes | Staring at the screen for multiple hours can strain your eyes and put you at risk of not seeing. | Take regular breaks and turn your attention away from screen from time to time | Moderate | Medium Risk | Low Medium
Computer breaking | Computer crashing or breaking is the worst thing that could happen and you can lose everything. | Make sure you’re your device is secure updated and has storage for it to run. | Very Unlikely | Major Risk | Medium
COVID-19 | Getting COVID-19 can put you at risk of not completing your project. | Follow government guidelines and stay safe plus warm | Likely | Fatality | High
Procastination | Intention to work but keep getting distracted and not actually getting any work done | Turn off mobile phones and devices and set yourself a time table that you can follow | Very Likely | low | Low
Losing your work | Losing your if you didn't save and laptop turning off | Make sure you save every piece of work when working and regularly pushing to git hub so its in the cloud | Likely | Medium Risk | Low Medium
Power cut/Internet down | If power cuts and Internet is down is a big risk of not completing your work and even losing your work | Work on a laptop instead as it doesn’t require continious power and make sure you save your work | Unlikely | Major Risk | High
Merge Conflicts | Merging code on same branches and causing merge conflicts | work on separate branches and push to the specific branch as well as communicate with team | Moderate | Medium Risk | Medium
Not meeting MVP | Not finishing the work and meeting requirements | Plan and split work effectively among group members whilst using the AGILE methodology | Unlikely | High | High
Conflict of interest | Dissagreement with group and not being able to complete tasks effectively | Assign a Scrum master and plan delegated tasks | Moderate | Medium Risk | Medium
Fire hazard | Fire catching and burning your house down | Keep computer well ventilated and keep flammable products away from sockets | Unlikely | High | Low Medium